## Sheet1
Project : " Empowering Women Vegetable Growers in Kalahandi, Malkangiri & Khurda Districts of Odisha "
S.No | Component | Unit Description | Physical Outlay (No.of units planned) As Per DPR |  |  |  | Action Plan
| Project Cost |  | Yr1 | Yr2 | Yr3 | Total | May, 15 | Jun, 15 | Jul, 15 | Aug, 15 | Sep, 15 | Oct, 15 | Remarks
1 | Project Inception
1.1 | Mahila Kisan profiling | No.of mahila kisan | 4500 | 1500 | 0 | 6000 |  | 1500
1.2 | DPR Preparation | lumpsum |  |  |  | 0 | [6 empty] | Completed
1.3 | Technical protocols documentation | lumpsum |  |  |  | 0 |  |  |  | 1 |  |  | Priniting completed & Video Production will be done
A | Subtotal |  | 4500 | 1500 | 0 | 6000
2 | Institution Building
2.1 | Mobilisation & Promotion of producer groups | No.of producer groups | 375 | 125 | 0 | 500 |  | 25 | 50 | 50
2.2 | Promotion of Vegetable growers cooperative | No.of producer Cooperative | 10 | 0 | 0 | 10 |  |  | 2 |  | 2 | 1
2.3 | Management support to vegetable growers cooperative | Coperative | 10 | 10 | 0 | 20 |  |  |  |  | 4 | 1
B | Sub total |  | 395 | 135 | 0 | 530
3 | Capacity Building
3.1 | Training module development : Print | No.of training modules | 20 | 2 | 0 | 22
3.2 | Training module development : audio-visual | No.of training modules | 4 | 1 |  | 5 |  | 1 |  | 1 |  | 2
3.3 | Training equipment & material | Nos | 4500 | 1500 | 0 | 6000 |  |  | 20 |  | 10 |  | Another 30 Projector will be purchased(1 Picco @150 Mahila kisan)
3.4 | Training to CRP | No.of CRP | 90 | 30 |  | 120 |  | 30
3.5 | Trainings to para-professionals | No.of para-professionals | 20 |  |  | 20 |  |  | 1 |  |  |  | 1 training on plant protection will be completd
3.6 | Training to Community | No.of community members | 4500 | 1500 |  | 6000
3.7 | Training to leaders & PRI | No.of leaders | 250 | 250 | 250 | 750
3.8 | Exposure visits of CRPs to immersion sites | No.of CRPs | 90 | 30 |  | 120
3.9 | Exposure visit of para-professional to immersion sites | No.of para-professionals | 20 | 20 | 0 | 40
3.1o | Exposure visit of Community to immersion sites | No.of mahila kisan | 500 | 500 | 0 | 1000
3.11 | Service charge to CRP (Excluding the resource fee received by them as trainers) | No.of CRPs | 100 | 120 | 120 | 340
3.12 | Service charge to para-professionals (Excluding the resource fee received by them as trainers) | No.of para-professionals | 20 | 20 | 20 | 60
3.13 | Review cum planning meeting for CRPs | Noof meeting per year | 12 | 12 | 12 | 36
3.14 | Annual district level interface | No of interface | 3 | 3 | 3 | 9
C | Sub total |  | 10129 | 3988 | 405 | 14522
4 | Community Investment Support
4.1 | Community Infrastructure | No.of Infrastructure units | 20 | 20 | 20 | 60
4.2 | Inputs to the mahila kisan (grant/subsidy/full loan) | No.of mahila kisan | 5000 | 100 | 0 | 5100
4.3 | Inputs to producer groups/ federation (grant) | No.of producer groups | 415 | 85 | 0 | 500
4.4 | Operational Fund of Producer federation | No.of producer federations | 10 | 0 | 0 | 10
4.5 | Other (Specify) |  |  |  |  | 0
| …. |  |  |  |  | 0
D | Sub total |  | 5445 | 205 | 20 | 5670
5 | Knowledge Management
5.1 | Identification of best practices | Lumpsum | 5 | 5 | 0 | 10
5.2 | Documentation of best practices | Lumpsum | 5 | 5 | 0 | 10
5.3 | Dissemination of best practices | Lumpsum | 5 | 5 | 0 | 10
5.4 | Other (Specify) |  |  |  |  | 0
| …. |  |  |  |  | 0
E | Subtotal |  | 15 | 15 | 0 | 30
6 | Monitoring & Evaluation
6.1 | Baseline survey | No. of HH to be covered | 4000 | 2000 | 0 | 6000
6.2 | Endline survey | No. of HH to be covered |  |  | 4000 | 4000
6.3 | Independent evaluation studies | No. of Studies |  | 1 | 0 | 1 |  |  |  |  | 1
6.4 | Public information disclosure | No.of information disclosure sites/places | 50 | 50 | 0 | 100 |  | 10 | 20 | 10
6.5 | Social Audit | No.of social audits | 10 | 10 | 10 | 30 |  | 10
6.6 | Facilitation and Mamangement of MIS | No of partner | 10 | 10 | 10 | 30
6.7 | Partners Review Meeting | No of meeting | 2 | 2 | 2 | 6 |  | 1 |  |  | 1
F | Sub total |  | 4072 | 2073 | 4022 | 10167
7 | Administration Expenditure (Maximum 5% of total project cost)
7.1 | Staff salaries | No of staff | 3 | 3 | 3 | 9
7.2 | Travel & conveyance | No of month | 12 | 12 | 12 | 36
7.3 | Stationary | No of month | 12 | 12 | 12 | 36
7.4 | Communication | No of month | 12 | 12 | 12 | 36
7.5 | Audit fees | peryear lumsump | 1 | 1 | 1 | 3
| …. |  |  |  |  | 0
G | Sub total |  | 40 | 40 | 40 | 120
H | Grand Total (A+B+C+D+E+F+G)

## Sheet2
Project : " Empowering Women vegetable Growers in Kalahandi, Malkangiri & Khurda Districts of Odisha"
Supported by : NRLM (Govt. of India) & OLM (Govt. of Odisha)
PIA : MADHYAM FOUNDATION , BHUBANESWAR
6 Monthly Action Plan
Action Plan
A.1 | Project Inception | Yr1 | Yr2 | Yr3 | Total | ACHIEVEMENT | May'15 | Jun'15 | Jul'15 | Aug'15 | Sep'15 | Oct'15 | Remarks
1.1 | Profiling of Mahilakisan | 4500 | 1500 | 0 | 6000 | 5000 |  | 500 | 500
1.2 | DPR Prparation | 1 |  |  | 1 | [7 empty] | Completed & Shared
1.3 | Technical protocol documentation |  |  |  | 0
1.3.1 | Printing of Booklet on Organic vegetable cultivation @ Rs30 per book | 3000 |  |  | 3000 | [7 empty] | Completed & Shared
1.3.2 | Prninting of reference book for CRP on SRI and Vegetable Cultivation @ Rs20 per book | 150 |  |  | 150 | [7 empty] | Completed & Shared
1.3.3 | Printing of Leaf let on SRI @ 8 per sheet | 5500 |  |  | 5500 | [7 empty] | Completed & Shared
1.3.2 | Documentation of technical protocol of Vegetable cultivation | 1 |  |  | 1
B. | Institution building |  |  |  | 0
2.1 | Mobilisation of & promotion & strnghthening of Producer grouops(SHG) | 375 | 125 | 0 | 500 | 375 |  | 30 | 50 | 45
2.1.1 | District level ToT on promotion of and strengthening of producer groups (SHG) for CRPs(30 CRPs perbatch) | 3 | 1 | 0 | 4 | 3 |  |  | 1
2.1.2 | Training on book keeping and management of producer group (For SHG leaders ) | 60 | 20 | 0 | 80 | 0 |  |  |  | 10 | 20 | 20
2.2 | Promotion of vegetable growers cooperatives |  |  |  |  | 0
2.2.1 | Central level TOT on promotion of vegetable growers Cooperative for Para professionals | 1 | 0 | 0 | 1 | 0 |  |  | 1
2.2.2 | District level TOT on promotion of vegetable growers Cooperative to SHG Leaders | 3 | 0 | 0 | 3 | 0 |  | 1 |  | 1 |  | 1
2.2.3 | Central level Training to Cooperative leaders on management of cooperatives | 1 | 0 | 0 | 1 | 0 |  |  |  |  | 1
2.2.4 | Registration & furniture exp per Cooperatives | 10 | 0 | 0 | 10 | 0 |  |  |  | 2 | 4 | 4
2.3 | Management to cooperatives
2.3.1 | Hand holding support to the cooperatives@ Rs 2000 per cooperative per month @2000 X 10 cooperative | 10 | 10 | 0 | 20 | 0 |  |  |  |  | 6 | 10
2.3.2 | Satationary and other related exp for Cooperative per cooperative @Rs 500 per month | 10 | 10 | 0 | 20 | 0 |  |  |  |  | 6 | 10
2.6 | Training to cooperative leaders on marketing of vegetable through cooperative | 3 | 3 | 0 | 6 | 0 |  |  |  | 1 | 1 | 2
3 | Capacity Building
3.1 | Development & Printing cost of Training modules | 20 | 2 | 0 | 22 | 0 |  |  | 5 | 5 |  | 5
3.2 | Development of training modules (Audio visuals ) | 4 | 1 | 0 | 5 | 0 |  | 1 |  | 1 | 1 | 1
3.3 | Training eqipments and materials (1 picco projector for per each 150 women farmers ) | 30 | 10 | 0 | 40 | 10 |  |  | 30
3.4 | Training to CRPs
3.4.1 | TOT on soil testing & Soil Helath Management | 3 | 1 | 0 | 4 | 3 |  | 1
3.4.2 | TOT on organic ways of vegetable cultivation & Crop planning | 3 | 1 | 0 | 4 | 3 |  |  |  | 1
3.4.3 | TOT on seed selection,treatment& preseravation,grading sorting and intermpreservation of vegetables | 3 | 1 | 0 | 4 | 3 |  | 1
3.4.4 | TOT on technological aspects of SRI | 3 | 1 | 0 | 4 | 3 |  |  | 1
3.4.5 | TOT on Plant protection and Intercultural operation on SRI | 3 | 1 | 0 | 4 | 1 |  |  |  | 3
3.4.6 | District level training to CRPs on marketing of vegetable through cooperative | 2 | 1 | 0 | 3 | 0 | [5 empty] | 2
3.5 | Training to Para Professionals
3.5.1 | TOT on soil testing & Crop Planning | 1 | 0 | 0 | 1 | 1 | [6 empty] | Completed
3.5.2 | ToT on soil health management with organic ways of vegetable cultivation | 1 | 0 | 0 | 1 | 1 | [6 empty] | Completed
3.5.3 | TOT on seed selection,treatment& preseravation,grading sorting and interim preservation of vegetables | 1 | 0 | 0 | 1 | 1 | [6 empty] | Completed
3.5.4 | TOT on Technological l aspects of SRI | 1 | 0 | 0 | 1 | 1 | [6 empty] | Completed
3.5.5 | TOT on Plant protection and Intercultural operation on SRI | 1 | 0 | 0 | 1 | 0 |  |  | 1
3.6 | Training to community
3.6.1 | Trainining on soil testing & soil health management | 95 | 5 | 0 | 100 | 72 |  | 20 |  | 8
3.6.2 | Training on organic ways of vegetable cultivation & Crop planning | 95 | 5 | 0 | 100 | 69 |  |  |  |  | 10 | 10
3.6.3 | Training on seed selection,treatment& preseravation,grading sorting and intermpreservation of vegetables towomen farmers | 95 | 5 | 0 | 100 | 61 |  | 10 | 10 |  | 10 | 5
3.6.4 | Training onTechnological aspects of SRI | 210 | 10 | 0 | 220 | 117 |  |  | 50 | 30
3.6.5 | Training onplant protection and intercultural operation on SRII | 210 | 10 | 0 | 220 | 3 |  |  | 60 | 60
3.6 | Integrated training to land less farmers on backyard Goatery | 15 | 5 | 0 | 20 | 12 |  |  |  |  | 3 | 5
3.7 | Training to leaders and PRI member |  |  |  | 0
3.7.1 | Orientataion on various project activities on project for PRI members | 10 | 10 | 10 | 30 | 10 | [5 empty] | 10
3.8 | Exposure visits of CRPS to Immersion Sites | 90 | 30 | 0 | 120 | 90 |  |  | 20
3.9 | Exposure visit of para professionals to immersion sites | 20 | 20 | 0 | 40 | 20 |  |  | 20
3.10. | Exposure visit of Community to immersion site | 500 | 500 | 0 | 1000 | 450 |  |  | 350
3.11 | Service charges to CRP | 100 | 120 | 120 | 340 | 0
3.12 | Service charges to Para professional | 20 | 20 | 20 | 60 | 0
3.13 | Monthly Review cum planing meeting for CRP | 120 | 120 | 120 | 360 | 0
3.14 | Annual district level interface | 3 | 3 | 3 | 9 | 1 |  |  |  |  | 2 | 1
4 | Input support
4.1 | Comunity Infrastucture support
4.1 | Hiring charges of Cooperative building @Rs 2000 per month per cooperative | 10 |  |  | 10 | 0 |  |  |  |  | 10 | 10
4.1.1 | Support of one comuputer set to each cooperative (unit cost Rs 40000/) | 10 |  |  | 10 | 0 | [5 empty] | 10
4.1.2 | Grant Support of soil testing kits@ two kits to each cooperative (producer federation) area ( to be handled by para Professionals )(cost per SHG) total cost Rs 200000/500 SHG =Rs400 | 20 |  |  | 20 | 18 |  | 2
4.2 | Inputs to Mahila Kisan |  |  |  | 0
4.2.1 | Support of Hand Hoe to 3000 Mahilakishans | 3000 |  |  | 3000 | 1450 |  |  | 500 | 500
4.2.2 | Support of widder to 1500 Mahila kishan (3 per each Producer Group ) | 1500 |  |  | 1500 | 147 |  |  | 1000
4.2.3 | Support of Improved sckiles to 5500 Mahilakishans | 5500 |  |  | 5500 | 322 | [5 empty] | 4000
4.2.4 | Grant Support for" O" engery House hold level Cool chamber for 3000 Vegetable growers @ Rs 1800 each | 3000 |  |  | 3000 | 169 |  |  |  |  | 1000 | 1000
4.3 | Input support to Producer Group |  |  |  | 0
4.3.1 | Grant support for purchasing of weight Measures for for 250 producer groups (Cost per group is Total 12.25lakhs/500 SHg) | 250 |  |  | 250 | 45 | [5 empty] | 100
4.4 | 0pertaional fund Producer Organisation |  |  |  | 0
4.4.1 | Operation fund for vegetable cooperative @Rs 30000 to each cooperative for working capital & promotion of seed bank ) | 10 |  |  | 10 | [6 empty] | 5
5 | Knowledge Managemnt
5.1 | Identification of Best practices | 5 | 5 | 0 | 10 |  |  |  | 2 | 2 | 2
5.2 | Documentation of Best Practices | 5 | 5 | 0 | 10 |  |  |  | 2 | 2 | 2
5.3 | Desimination of Best Practices | 5 | 5 | 0 | 10 |  |  |  | 2 | 2 | 2
6 | Monitoring & Evaluation
6.1 | Base line survey | 4000 | 2000 | 0 | 6000 |  |  | 1000 | 1000
6.2 | End Line Survey | 0 | 0 | 4000 | 4000 | [7 empty] | it will be done in 3rd yr
6.3 | Indepentent evaluation study | 0 | 1 | 0 | 1 | [7 empty] | Plan in Dec, 15
6.4 | Public information disclosure | 50 | 50 | 0 | 100 |  |  |  | 30 | 30
6.5 | Social Audit | 10 | 10 | 10 | 30 |  |  | 10
6.6 | Facilitation and Mamangement of MIS | 10 | 10 | 10 | 30
6.7 | Semi annual Partners Review meeting | 2 | 2 | 2 | 6 |  |  | 1 |  |  |  | 1
7 | Administration Expenditure
7.1. | Staff salaries | 12 | 12 | 12 | 36
Crop Coverage
1 | No of Mahila Kisan Practicing SRI | 4000 | 1500 |  | 5500 | 2015 |  | 4000
2 | No of Mahila Kisan Practicing Organic ways of Vegetable Cultivation | 2000 | 1000 |  | 3000 | 200 |  |  |  |  | 1000